## Hoja1
TASK | hours |  | Total of hours | 27.5
Dividing unique table in some others as number of temperature systems | 0
* Independent stages: outdoor air temperature, ocuppancy | 0.5 |  | oDesk rate | 22 | usd
* Air handle unit: discharge temp, pressure, damper possition, | 0.5 |  | Total budget | 605
* chilling water system | 0.5
* hot water system | 0.5
* dupm opening system | 0.5
Fixing import module | 6
Explanatory error message if csv file is not properly working | 1
Excel template for the uploading module | 2 | Some tests should be done
Get the user id from an XML format data provided by client | 1 | CLIENT MUST PROVIDE THIS XML, OR JSON OR ACCESS TO HIS DATABASE
Create an API that incorporates user id as part of the URL | 0 | Included in previous task.
Redirect to "subscribe" page if user does not exist (Create a new user id for colums) | 1
Create "datasets" table - > some different sets of data & foraing key on dataset | 2
drop-down list with the names of all their existing sets | 2
Allow user to import data as new dataset or update existing one | 2
display data tables grouped by temperature system | 4
4. Allow the user to change the chart type (bar, lines, dots) | 2
Allow user to rename a dataset, or delete it altogether | 1
7. Support printing a chart | 1
DISCARDED TASKS | REASON
from column 3 onward, they will have to pick from the dropdown list go one column at a time | Bunches of data can be easily selected or left as emtpy in the Excel template
5. Port the chart widget to run locally on a user's machine | It will be left at the end of the project.
display of the data into smaller groups of columns (in alphabetical order), | Instead of alphabetical groups data will be sorted according to temperature system (chilling water, fan systems, etc)