## HOME
Please click on name to see details
Description | hours | Estimated time of delivery
Dataset | 19 | 3 | days
Charts | 25 | 4 | days

## Dataset
DESCRIPTION | HOURS | Back to HOME | Total hours | 16.5 | Fixing bugs (10%+) | 19
Basic structure and initian settings: includes css library twitterBootstrap, js library jquery, php framework Laravel (recommended) and basic HTML design. | 0.5
Database setting: creating tables and its relations | 2
Table "users" (data provided by client)
Table "measurements" with 32 columns plus foreing key
plus unique column "name of set of data", plus column
temperature unit (Farenheit vs Celsius), plus timestamp
created_at and updated_at (useful when resorting data).
plus company's opening and closing times, plus maybe
the company's name.
All these columns should be included except they already
exist.
Data uploading method (csv file) | 2
Structure validation (al csv must have the same data structure)
MS Excel template with error barriers (suggested) | 1
Duplicated values filters (error barriers) | 1
Adjust all data from same timestamp in same row (suggested)* | 1
instead of having same timestamp data on different rows.
It is easily done with logic functions.
Celsius to Farenheit conversor | 0.5
Missed temperature data autocompletion and calculation | 1
Sorting data according to timestamp (user do not need to sort it) | 0.5
Allowing user to resort data after uploaded | 1
HTML data visualization and edition ** | 4
Inline data edition (should be password
protected or only admin profile restricted)
Change, update, add and delete data (manually) | [6 empty] | JANUARY
Code commenting. | 2
FEBRUARY
* With logic functions, data entered on different moments and that | [6 empty] | MARCH
correspond to same timestamp can be saved on same row. This is highly | [6 empty] | APRIL
recommended as database is cleaner, besides data analysis and charting | [6 empty] | MAY
are not affected at all. | [6 empty] | JUNE
** Data edition should have any protection level as there might be | [6 empty] | JULY
a responsible when changing data previously recorded from some | [6 empty] | AUGUST
trustful source. | [6 empty] | SEPTEMBER
OCTOBER
I could also provide a MS-Excel template with fields that allow only | [6 empty] | NOVEMBER
specific formats, such as percent, dates, fixed numbers, float numbers | [6 empty] | DECEMBER
and so on, as Excel provides great tools for limiting data types
including simple help boxes.
Examples below
TRY TO ENTER DATA DIFFERENT TO PERCENT NUMBER
TRY TO ENTER DATA DIFFERENT TO MONTHS
ONLY INTEGER AND POSSITIVE NUMBERS ALLOWED
PLEASE BE AWARE THAT SHOWN FIELDS ARE JUST EXAMPLES
THAT MIGHT NOT MATCH WITH THE PROJECT'S CRITERIA

## Charts
DESCRIPTION | HOURS | Back to HOME | Total hours | 23 | Fixing bugs (10%+) | 25
Setting chart library amCharts.js | 0.5
HTML basic design (TwitterBootstrap css) | 0.5
Setting options for X and Y axis | 2
Setting array of data to be displayed. | 2
- Filtered by user (cannot see others' data)
- 24 hours / 2 hour interval
- 12 hours / 1 hour interval
- 1 hours / 5 minutes interval
- 18 types of charts | 18

## Hoja1
Questions
1. Laravel framework possible?
2. Data structure
3. User's description
4. Recommended columns (go to existing and named colums)
5. What generates the csv file? Some sort of software or an electronic device I guess.
6. Why some data corresponding the same timestamp might be uploaded in different moments?
7. Why should the user edit data?
8. Which items previously mentioned on Excel file are not aligned with project?
9. Besides indentation and commenting classes, do you prefer any